## Cover
Workbook for Assignment 1

## Charter
Project Charter
Project Charter
Element | Description | Details
Project Name: Diabetes Care | Unique identifier for project | Patient ID - Clinic ID
Problem Statement | Define the current state | Incompatible EMRs, Varied treatments,Lack of Infrastructure
Objective | What improvement is targeted? | Standarize Treatments, synchronize EMRs ,Use of telemedicine for patient monitoring and education
Process Metrics | Baseline metrics and targets so that improvements can be tracked
| Metric | Baseline | Target
| Standardizing Treatment | 4 months | 2 months
| Use of Tele-medicine | 40 days | 10 days
| Wait Time for Patients | 15-20 mins | 3-5 mins
| Unique EMR | 3 months | 40 days
Notes: The clinics need to develop the infrastructure over a period of 3-4 months to support Use of Telemedicine & also for standardizing the treatments across all the clinics.Telemedicine trialled first at a clinic then used at other clinics. Instead of using 2 EMR's, having a unique EMR with visualization support would help both the patient and the clinic. This will aid in aggregating the data & getting it to a single database. Then we can do the visualization on the data.
Team Members: Ankur & SriNithya
Project Start Date: 10/26/2017

## Define the Problem
Define the Problem Tool

## Critical to Quality
Critical to Quality
Goals | Drivers | Critical to Success | Process Step | Root Causes of Waste | What do I know | What do I need to know | How will I learn/Potential Tools | Next Steps/owner | Constraints/Issues
Resource Allocation ( Physic-ians , Nurse & assistants) | Uniform - Smooth Functioning of Clinics | Not sure | Division of HR according to facility & work amount |  | Lack of staff | No. of Patients using a particular clinic | Scheduling tools like Doodle, Clara | Consistent Scheduling | Staff Training
Standardize Treatment | Maintaining Quality | Yes | Unique EMR & standard Infrastructure & Process | Incompatibility between EMR's | We have 2 EMR's | If we can standardize it | EMR with visualization tool like a Praxis EMR or WebPT | Have a unique Patient ID - Clinic ID | Time Constraint depending on no. of patients in a clinic
Use of Telemedicine | Educate & monitoring Patients & reduces their wait time & 24*7 | Yes | Develop infrastructure & staff training |  | Need for Infrastructure | No of patients | Telemedicine tool with digital imaging and high-bandwidth communication

## Standard Work
Standard Work
Step | Task | Who | Frequency | Number | Accountability
1
2
3
4
5
6
7
8
9
10

## FMEA
Failure Modes and Effects Analysis
Failure | Root Cause | Frequency | Risk Level | Remedy | Timeline | Complete
Patient Leaving the facility | No. of Physicians | Depends on time of the season | High | TeleMedicine & Increased no. of physicians | 30 days

## Tracker
Tracker
Category | Initiative/Activity/Project | Pillar | Start Date | Status | Complete Date | Comments | Outcomes | Next Steps
Communications
Operations
Facilities
Leadership/Team
Clinical
Educational
Marketing

## ABCD
ABCD
Accomplishments | Benefits
Concerns | Do Next